## Sheet1
COSC1076 ¦ Semester 1 2021
Assignment 2 ¦ Weekly Update Tracking Sheet
Group Name:
Group Member: | Liam Whitaker (s3899679) |  | Progress Classes: | Ahead
Group Member: | B |  |  | On-track
Group Member: | C |  |  | Behind
Group Member: | D |  |  | Way Behind
Tutor:
Class:
|  | Week 7 | Goals | Tutor Notes | Indidvidual Updates | =$B$5 | B | C | D
|  |  | Group Formed |  | Weekly Contribution | Created the Git repository and a team group.
|  |  | MS Team created |  | Issues | Tested positive for COVID, was not able to attend classes for the week: randomly assigned a group, with members from other classes.
Git Repo created
[5 empty] | Other Notes | Git repo is initiallised with all the skeleton code
and assignment info
|  | Progress | On-track
|  | Week 8 | Goals | Tutor Notes | Indidvidual Updates | Liam Whitaker (s3899679) | B | C | D
|  |  | Choice of where to use linked list, vector & array |  | Weekly Contribution | very little
|  |  | Initial Design of ADTs (classes and potential methods) |  | Issues | still unable to attend class.
|  |  | Main menu |  | Other Notes
User Prompt (for gameplay), but no/minimal error checking
Linked List implementation
Implementation(s) or suitable ADTs wrapper for the use of vector and arrays, game logic not required
ADT implementation for storing information, game loop logic not required
|  | Progress | Way Behind
|  | Week 9 | Goals | Tutor Notes | Indidvidual Updates | Liam Whitaker (s3899679) | B | C | D
|  |  | Load/Save to/from data strucutres (doesn't require integration with main menu or game loop) |  | Weekly Contribution | -
|  |  | Initialisation of data strctures for new game |  | Issues | -
|  |  | Write Tests Cases for common uses |  | Other Notes
Gameplay for single round
|  | Progress | Way Behind
|  | Week 10 | Goals | Tutor Notes | Indidvidual Updates | Liam Whitaker (s3899679) | B | C | C
|  |  | Fully complete implementation and error free |  | Weekly Contribution | Completed LinkedList ADT, including implementation of Node and Tile classes. Menu loop created. Ready for game implementation
|  |  | Full error checking of user prompt |  | Issues | Rest of group unresponsive. Far behind schedule.
Other Notes
Final Tests
Group Report Written
|  | Progress | Way Behind